## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Adithi Varda | 2026-07-09 | Language detection failed for some pasted Java code. | Sprint 1 | Adithi Varda | Functional | Improved language detection logic and tested with multiple code samples. | 2026-07-10 | Closed | Issue resolved successfully.
2 | Adithi Varda | 2026-07-11 | Python syntax validation did not handle invalid syntax correctly. | Sprint 1 | Adithi Varda | Functional | Added AST-based syntax validation and exception handling. | 2026-07-12 | Closed | Validation working correctly.
3 | Adithi Varda | 2026-07-16 | Security Agent missed hardcoded API keys in some test cases. | Sprint 2 | Adithi Varda | Functional | Enhanced pattern matching for API keys and secrets. | 2026-07-17 | Closed | Detection accuracy improved.
4 | Adithi Varda | 2026-07-18 | Code quality score calculation required better balancing. | Sprint 2 | Adithi Varda | Enhancement | Refined scoring logic based on issue severity. | 2026-07-19 | Closed | Balanced scoring achieved.
5 | Adithi Varda | 2026-07-22 | Gemini API quota/model issues prevented AI responses. | Sprint 3 | Adithi Varda | Integration | Migrated AI Assistant from Gemini API to Groq API while retaining the RAG pipeline. | 2026-07-22 | Closed | AI Assistant working successfully.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others